## taxi_system_20161214_1146
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Owned By | Owned By | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status
135665801 | Registeration | customer login module | 1 | Nov 30, 2016 |  | feature | 3 | started | Nov 30, 2016 |  |  | kokcc | as a customer, i should able to register a login id, so that i'm able to login and system able to get my information | https://www.pivotaltracker.com/story/show/135665801 | BooHan Khoo | koh choon teng | Let customer to key in their information | not completed | Add customer information accordingly to the database | not completed | Prompt successful message | not completed
135665831 | Login | customer login module | 1 | Nov 30, 2016 |  | feature | 3 | started | Nov 30, 2016 |  |  | kokcc | as a customer, i will register as member and login to the system, so that i can make reservation using my id | https://www.pivotaltracker.com/story/show/135665831 | kokcc | khor weisan | Let user to enter their user id and password | not completed | Verify the id and password in database | not completed | Prompt successful message | not completed
135666955 | Add new reservation | reservation module | 1 | Nov 30, 2016 |  | feature | 3 | started | Nov 30, 2016 |  |  | kokcc | as a customer, i should able to add new reservation, so that i can make booking online | https://www.pivotaltracker.com/story/show/135666955 | kokcc | Sherlyn Khoo | Let user to key in pick up/ drop off location and pick up time | not completed | Check location, time and driver availability in database | not completed | Show distance and time needed | not completed | Let user direct proceed to payment | not completed | Add the pick up location and destination to favorite | not completed
135667411 | Add new payment | payment module | 1 | Nov 30, 2016 |  | feature | 2 | started | Nov 30, 2016 |  |  | kokcc | as a customer, i should able to add payment online, so that i can pay it using my credit card | https://www.pivotaltracker.com/story/show/135667411 | BooHan Khoo | Sherlyn Khoo | Get reservation details from database | not completed | Let user to key in credit card details | not completed | Generate an online receipt | not completed
135668277 | Add new Driver | maintain driver module | 1 | Nov 30, 2016 |  | feature | 2 | started | Nov 30, 2016 |  |  | kokcc | as a staff, i should able to add new driver, so that new driver information will be recorded in system. | https://www.pivotaltracker.com/story/show/135668277 | koh choon teng | Sherlyn Khoo | Let user to enter driver information | not completed | Insert all information into database | not completed | Prompt successful message | not completed
135668455 | Update Driver information | maintain driver module | 1 | Nov 30, 2016 |  | feature | 2 | started | Nov 30, 2016 |  |  | kokcc | as a staff, i should able to update driver information, so that i can help driver to update their information in system up to date. | https://www.pivotaltracker.com/story/show/135668455 | koh choon teng | kokcc | Retrieve the information from database | not completed | when click update, update all the information in database | not completed | Prompt successful message | not completed